## QA Review (hidden)
Effort Estimate Checklist
Review Date:
Reviewer :
Id | Task | Yes/No | Comments/Action based on this version
1 | Have tasks/activities been listed, categorised and estimated?
2 | Have best case (minimum) and worst case (maximum) effort estimates been provided for the tasks/activities
3 | Has a resource plan been created to support the effort estimate? This should include role and number of days allocated per day, work or month
4 | Have the key assumptions that were used to produce the effort estimation been listed?
5 | Have the key dependencies that we have based our estimate on been listed?
6 | Have the key known risks been listed?
7 | Is it clearly stated how contingency in the effort estimate has been accounted for?
Price Release Checklist
Review Date:
Reviewer :
Id | Task | Yes/No | Comments/Action based on this version
1 | Have we calculated the price from a credible, resource based effort estimate?
2 | Is the scope clearly defined?
3 | Are the key assumptions & dependencies noted?
4 | Has the appropriate rate card been used to generate the price?
5 | Have expenses & VAT been noted as excluded or excluded from the price?
6 | Has the Gross Margin (GM) and GM% been calculated?
7 | Has the commercial and competitive context been considered when adjusting the price and GM%?

## Legend
LEGEND:
Dependency Status:
Note: | Dependencies for an API are either Pending or Complete. API delivery requires all dependencies to be Green.
RED | Dependency is PENDING (Not complete and blocking planned API Delivery)
AMBER | Dependency PENDING (In-Progress or Partially Complete but not finalised).
GREEN | Dependency is COMPLETE
API RAG status:
Note: | API RAG status indicates readiness of an API for formal testing (taking in to account Design Dependencies, Development & Unit-testing progress, packaging of code and deployment into TEST Environment as part of a managed Release).
RED | Dependencies PENDING or ISSUES blocking progress. Cannot complete Development & Unit Testing by planned date.
AMBER | Dependencies PENDING. Development & Unit-testing IN-PROGRESS but at risk. OR Dependencies COMPLETE but there are ISSUES needing resolving.
GREEN | Dependencies COMPLETE. Development & Unit-testing IN-PROGRESS. No blockers. OR All COMPLETE & API deployed to TEST Environment.
Milestone RAG status:
Note: | Project RAG status indicates overall status of the Project, taking in to account status of Deliverables, Target Milestone dates and Commercial Budget.
RED | Milestone blocked
AMBER | Milestone at risk
GREEN | Milestone on track or complete
Project RAG status:
Note: | Project RAG status indicates overall status of the Project, taking in to account status of Deliverables, Target Milestone dates and Commercial Budget..
RED | Major issues outstanding, no identified resolution plan. Project progress impacted.
AMBER | Major issues outstanding, resolution plans in place. Project progress at risk.
GREEN | Project on track, no major issues impacting progress outstanding.

## Key Milestones
S.No | Milestone | Start Date | Target Date | Revised Target Date | Date Delivered | Status | RAG | Comments
1 | Design | 2025-05-01 | 2025-05-09 | 2025-07-04 | 2025-07-04 | Completed | G
2 | Build & Unit Testing | 2025-05-08 | 2025-06-20 | TBC |  | In Progress | R | Change in Scope - Mezze has asked for new updates to JASON schema's
3 | SIT/UAT Testing Support | TBC | TBC
4 | PROD Go-Live & Hypercare | TBC | TBC

## Deliverables
ID | Milestone | Deliverable | Status | Start Date | Target Date | Revised Target Date | Date Delivered | RAG | Comments
1 | Design | Build Design for ePod/Mezze Experience API | Completed | 2025-05-05 | 2025-05-06 | 2025-06-20 | 2025-06-20 | G | 13/06: Details of object store to store message ID's and validate against route complete. 23/05: Build design document completed. 16/05: Completed initial version of Build design document and shared it for internal review, will keep updating untill all the dependencies related to this API are unblocked. 08/05: Bell has provided sample schema, However waiting for actual Schema Definitions for Stocks Interface & Route Complete from Mezze team.
2 |  | Build Design for System 21 System API | Completed | 2025-05-05 | 2025-05-06 | 2025-06-27 | 2025-06-27 | G | 23/05: Will be on hold till the signed off mapping are provided. 22/05: Need all System 21 table Names & column names and the table relationships if they are dependent or not 15/05: We have 14 tables in total, out of which 1 table data will be provided by Dan today. 07/05: Waiting for mappings, Bell to check with business partners internally and get back.
3 |  | Build Design for Scheduler App | Completed | 2025-05-06 | 2025-05-08 | 2025-07-04 | 2025-07-04 | G | 13/06: Watermark message structure details to be added into LLD. 29/05: Updated flows to add data lake conenctor to perform append operations. Also Orders - WIP 23/05: Completed, and in internal review. 15/05: Started working on initial version. 07/05: Waiting for mappings, messages & Schema details.
4 |  | Build Design for File mover system API | Completed | 2025-05-06 | 2025-05-07 | 2025-07-04 | 04-07-2025 | G | 29/05: Updated Sequence diagram, need to discuss with Bell on final confirmation.
5 |  | Build Design for Fresh Service System API | Completed | 2025-05-07 | 2025-06-13 |  | 2025-06-11 | G
6 | Build & Unit Testing | Project Setup: o Create Git repositories o Create user stories and tasks o Create pipelines o Create Queues and exchanges for reliability o Integrate with Azure AD as OAuth provider. | Completed | 2025-05-01 | 2025-05-09 | 2025-05-23 | 2025-05-23 | G | GIT Repositories: Got access to repository. User Stories & Tasks: Waiting for Rebecca to create tasks in JIRA. Ranjith will collate all the requirements and share it with SWB team, as per the discussions with Bell. Bell to acknowledge. Pipelines: Need to check once after API is build and while deploying. Queues & Exchanges: Got access to Queues & Exchanges. Azure AD with OAUTH: Azure OAUTH configuration is pending.
7 |  | RAML Design for ePod/Mezze Experience API | Completed | 2025-05-08 | 2025-05-08 |  | 2025-05-08 | G | 09/05: Completed RAML - At the moment we are using client enforcement headers once we get OAUTH we will update the headers. 08/05: Started working on RAML
8 |  | RAML Design for System 21 System API | Completed | 2025-05-09 | 2025-05-09 |  | 2025-05-09 | G | 09/05: Completed RAML. 08/05: Health check end point is required for this.
9 |  | RAML Design for Scheduler App | Completed | 2025-05-19 | 2025-05-19 | 2025-05-21 | 2025-05-21 | G | 21/05: RAML completed. 15/05: Health check end point is required for this. Bell to confirm on mule scheduler app name (API name).
10 |  | RAML Design for File mover system API | Completed | 2025-05-21 | 2025-05-28 | 2025-05-30 | 2025-05-30 | G | 30/05: Completed RAML 23/05: RAML In Progress, need to work on call back URL end point.
11 |  | RAML Design for Fresh Service System API | Completed | 2025-05-27 | 2025-05-28 | 2025-05-06 | 2025-06-04 | G | 04/06: Completed RAML
12 |  | Build for ePod/Mezze Experience API | Completed | 2025-05-09 | 2025-05-14 | 2025-06-27 | 2025-06-27 | G | 27/06: Build completed, deployed to DEV & unit testing completed. 20/06: Waiting for mapping field limitation decisions from SB. 05/06: Working on Keyvault implementation & solution to save message id's and validate it against the route complete messages. 28/05: Shared API specifications with SB, Mezze will go through and get back for any further changes (if any). Need to implement Azure Keyvault & CDM Alerting. 23/05: Received first version of schema's, team is working on the same. 22/05: Waiting for signed of Schema Specifications & finalize queue details to publish to System21 system API. 20/05: Got schema details for Route complete. 19/05: Pipeline deployment is failing due to JDK issue for mule 4.9. checking on the same. 14/05: Build completed for happy path, have to start working on logging, error handling, alerting etc once system 21 system API is done. 07/05: Agreed that we are going with cloud event model. Delivery Notes - All data Available to start. Stocks Interface - Bell has provided sample schema on 08/05, However waiting for actual Schema Definitions for Stocks Interface & Route Complete from Mezze team. Route Complete - Samples & Schemas are required. Will receive by End of Week from SWB.
13 |  | Build for System 21 System API | Completed | 2025-05-12 | 2025-05-20 | 2025-07-03 | 2025-07-03 | G | 27/06: Build completed, Improving pipelines to maintain azure key vault credentials. 20/06: Waiting for mapping field limitation decisions from SB. 23/05: Signed off mapping specification may take more time, discussed with SB and agreed to keep this on hold. 21/05: DB2 UI, Azure Portal to verify transactions via developer workstation. 19/05: Waiting for Azure Table storage Information, to store route id’s & Signed Off Mapping Specifications for Delivery Notes, Stocks & Route Complete interfaces. 16/05: Need all System 21 table Names & column names and the table relationships if they are dependent or not. 14/05: Got access to DB2. Started working on this. 07/05: Waiting for DB2 Connection details - Bell has raised a ticket (#64996) to get the details from internal team.
14 |  | Build for Scheduler App (Order, Item & Customer - Existing APIs) | In Progress | 2025-05-09 | 2025-05-22 | TBC |  | R | 08/08: Change in Scope - Mezze has asked for new updates to JASON schema's 28/07: p-sb-scheduler-app deployed to DEV after recent schema changes to Customers, Items & Orders. Smoke testing in Progress 27/06: Functional requirements - Completed, Non-Functional requirements implementation - In Progress. 20/06: OAUTH implementation to connect to filemover. 05/06: Working on Keyvault & Cosmos DB integration implementation & Orders Implementation. 30/05: Implemented flows for customer and Items, to start working on orders. 23/05: Received Customer mappings from SB. 21/05: Confirmation on Order Process API changes and implementation plan to process it in scheduler APP. 20/05: Need REST API OAUTH credentials for Azure BLOB for append operation & Azure Table storage Information, to store watermarks 19/05: Waiting for Signed off Mapping Specifications & Filter criteria for Order, Item & Customer. 15/05: Able to connect to Azure BLOB. Started working on error handling scenarios. 09/05: Got Azure BLOB storage connection details need to check on the connection happens. 08/05: Working on Item and customer for now. 07/05 - 1. Bell has sent mail to sent to Shaun & Jonathon on Azure BLOB storage Connection Details Waiting for their response. 2. Bell/Dan to provide mappings 3. Bell/Dan to provide Filter criteria 4. Need name confirmation for scheduler App.
15 |  | Build for File mover system API | Completed | 2025-05-19 | 2025-05-23 | 2025-07-04 | 2025-07-04 | G | 27/06: Functional requirements - Completed, Non-Functional requirements implementation - In Progress. 06/06: Working on app/file/move endpoint Subscription & Need to start job status endpoint. 30/05: Waiting for design conclusions from SB, Currently working on job status endpoint & rework on app/file/move endpoint in accordance with design changes 23/05: Working on message structures. 19/05: Need SFTP details. 14/05: Azure BLOB connection is successful. 09/05: Got Azure BLOB storage connection details need to check on the connections happens. 07/05: 1. Waiting for Azure Blob Details & SFTP Details from SWB 2. Need name confirmation for scheduler App.
16 |  | Build for Fresh Service System API | Completed | 2025-05-23 | 2025-05-30 | 2025-06-20 | 2025-06-20 | G | 13/06: Incorporate some changes based on the LLD. Work on Munits and Check AppInsights. 06/06: Completed Implementation 19/05: Need Fresh service connection details.
17 |  | Build for AX-Sales Order SAP | Completed | 2025-06-10 | 2025-06-18 |  | 2025-06-18 | G
18 |  | Build for AX-Item SAP | Completed | 2025-06-10 | 2025-06-13 |  | 2025-06-13 | G
19 | UAT Testing Support | Deploy the code into UAT Environment and provide the testing support for ePod Experience API |  | TBC | TBC
20 |  | Deploy the code into UAT Environment and provide the testing support for System 21 System API |  | TBC | TBC
21 |  | Deploy the code into UAT Environment and provide the testing support for Scheduler App |  | TBC | TBC
22 |  | Deploy the code into UAT Environment and provide the testing support for File mover system API |  | TBC | TBC
23 |  | Deploy the code into UAT Environment and provide the testing support for Fresh Service System API |  | TBC | TBC
24 |  | Deploy the code into UAT Environment and provide the testing support for AX-Sales Orders API |  | TBC | TBC
25 |  | Deploy the code into UAT Environment and provide the testing support for AX-Items API |  | TBC | TBC
26 | PROD Go-Live & Hypercare | Production Deployment Support: o Creating runbooks o Checking dependencies o Generating the deployment JAR files using devops pipelines o Assistance with creation of CAB ticket |  | TBC | TBC
27 |  | Deploy the code into Production Environment |  | TBC | TBC
28 |  | KT to BAU Team |  | TBC | TBC

## Risks
ID | Date of Identification | Description | Priority | Owner | Impacted Areas / Detail | Mitigation Plan / Comments | Status | Target Date | Closer Date
1 | 2025-05-06 | Integration challenges with legacy systems (System 21, DB2) | High | Bell/Dan | Delays to Integration challenges with legacy systems could leads to development and timeline delays | Reconsider the design of System API. | Closed | 2025-05-14 | 2025-05-14
2 | 2025-05-06 | Key Vault access/configuration issues | High | Bell/Dan | Delays to receiving access for Key Vault access/ configuration issues could leads to development and timeline delays | Confirm permissions and secrets setup in initial sprint | Closed | 2025-05-21 | 2025-05-21
3 | 2025-05-06 | Issues with SFTP/Azure Blob storage file transfers (e.g., connectivity, Access) | High | Bell/Dan | Delays to receiving access for SFTP/Azure Block storage could leads to development and timeline delays | Conduct early connectivity testing with test files | Became an issue | 2025-05-09 | 2025-05-23
4 | 2025-05-06 | Rework on API design & build due to unclear requirements/mapping specifications | High | Bell | Delays in receiving signed of Schema/mapping specifications & design confirmations could lead to design & development timeline delays | Involve product team early in design reviews | Became an issue | 2025-05-12 | 2025-05-23
5 | 2025-05-06 | Fresh Service integration API design decisions yet to conclude | Medium | Bell | Delays in receiving Fresh Service integration API design confirmations could lead to design timeline delays | Validate integration endpoints and create mock alerts for testing | Closed | 2025-05-12 | 2025-05-22
6 | 2025-05-06 | Project timelines are tightly constrained while key requirements and system access details remain undefined or pending clarification. | High | Bell | Risk of rework or scope creep due to late discovery of functional and technical requirements. Increased chance of project overrun and missed milestones | Conduct a requirements clarification workshop with SMEs and stakeholders. Define a “Requirements Freeze” date and Parallel-track access requests to avoid idle time during Design/Development stages. Establish checkpoints for critical dependencies and raise blockers in daily/weekly meetings. | Became an issue | 2025-05-12 | 2025-05-23
7 | 2025-05-06 | Citrix access blocking DEV team to perform local testing | Medium | Bell/Dan | Delays to receiving access to Citrix could leads to development and timeline delays | Provision Temporary Local Access, Escalate and Prioritize Access Requests | Became an issue | 2025-05-12 | 2025-05-23
8 | 2025-05-06 | All the dependencies to be resolved within the agreed time lines | Medium | Bell | Project time lines will be impacted and also developers has to wait for the dependency to be cleared to move forward | No Mitigation Plan in plate as Dependency Clearence will be the most requirement to make the progress from Prolifics. Prolifics PM to closely work sith SB team. | Became an issue | 2025-05-16 | 2025-05-23
9 | 2025-06-06 | No confirmation received from the client regarding SIT and UAT testing timelines. | High | Bell | Potential delays in the overall project schedule due to lack of clarity on testing phases. | Follow up with the client to obtain testing timelines; proceed with preparatory activities (if any) in parallel to minimize idle time. | Became an issue | 2025-06-20 | 2025-06-23
10 | 2025-07-28 | Ongoing scope creep due to frequent schema and mapping changes, leading to rework, increased effort, and potential delays in delivery. | High | Bell | Potential delays in the overall project schedule which is impacting overall budget & cost control. | Freeze schema/mapping after design sign-off unless changes are business-critical & Establish a formal change control process for schema/mapping modifications | Became an issue | 2025-08-01 | 2025-08-01

## Assumptions
S.No | Description/Details
1 | The estimate is based on the HLD and LLD documents shared by Customer.
2 | Performance testing and security testing are out of scope.
3 | Exceptions in the workflow will be logged in MuleSoft logs.
4 | Firewall changes and network Connectivity between MuleSoft and different systems is owned by the Customer.
5 | Event sequencing and de-duplication requirements are out of scope.
6 | MuleSoft out-the-box monitoring only. Alerts are raised in fresh service. Alert event will follow cloud event data model.
7 | Alerting framework would use AnyPoint MQ for reliability.
8 | The Solution will use the existing Samworth error handling and logging solution. Logging includes integration with Azure App Insights.
9 | Mapping complexity between ePod, CDM and System 21 is simple.
10 | Connection with System 21 will be using DB2 connector and stored procedure.
11 | Azure AD will be used as OAuth provider for authentication.
12 | All messages are less than 10mb
13 | All new APIs will be built on 4.9 runtime and Java 17.
14 | Creation of CH 2.0 infrastructure and any VPNs is out of scope.
15 | Staging of delivery routes in object store is out of scope. These routes will be staged outside MuleSoft.
16 | Alert aggregation/deduplication is done by Fresh Service and not MuleSoft.
17 | Order Process API and AX Order System API exposes REST API to fetch non-food for now orders. This endpoint will be reused to fetch orders.
18 | The ePod Experience API will break down events into separate units—such as waste, returned products, sales, and delivery notes—allowing each to be processed independently.
19 | Pagination is out of scope.
20 | Grouping of alerts based on error type and frequency will be in Fresh Service.
21 | Update existing APIs to publish alert events to exchange and not queue.
22 | Reuse existing Samworth CI/CD pipelines to deploy APIs. No effort added for DevOps.
23 | Reuse Samworth Azure boards and wiki for issue tracking and documentation
24 | Out of Hours or weekend working is not required.

## Issues
ID | Issue | Severity | Raised Date | Owner | Impact / Comments | Status / Actions | Complete Date
1 | All the dependencies to be resolved within the agreed time lines | Medium | 2025-05-23 | Bell | Project time lines have impacted and also developers are waiting for the dependency to be cleared to move forward | Dependency Clearence will be the most requirement to make the progress from Prolifics. Prolifics PM to closely work sith SB team. | TBC
2 | Issues with SFTP/Azure Blob storage file transfers (e.g., connectivity, Access) | High | 2025-05-23 | Bell/Dan | Delays to receiving access for SFTP/Azure Block storage have led to development and timeline delays | Conduct early connectivity testing with test files. | 2025-06-06
3 | Rework on API design & build due to unclear requirements/mapping specifications | High | 2025-05-23 | Bell | Delays in receiving signed of Schema/mapping specifications & design confirmations have led to design & development timeline delays | Involve product team early in design reviews. | 2025-06-13
4 | Project timelines are tightly constrained while key requirements and system access details remain undefined or pending clarification. | High | 2025-05-23 | Bell | Team had to rework on scope creep due to late discovery of functional and technical requirements which increased the likelihood of project overruns and missed milestones. | Conduct a requirements clarification workshop with SMEs and stakeholders. Define a “Requirements Freeze” date and Parallel-track access requests to avoid idle time during Design/Development stages. Establish checkpoints for critical dependencies and raise blockers in daily/weekly meetings. | 2025-06-13
5 | Citrix access blocking DEV team to perform local testing | Medium | 2025-05-23 | Bell/Dan | Delays to receiving access for Citrix have led to development & unit testing timeline delays | Provision Temporary Local Access, Escalate and Prioritize Access Requests | 2025-06-13
6 | No confirmation received from the client regarding SIT and UAT testing timelines | High | 2025-06-06 | Will | Potential delays in the overall project schedule due to lack of clarity on testing phases. | Follow up with the client to obtain testing timelines; proceed with preparatory activities (if any) in parallel to minimize idle time. | TBC
7 | Ongoing scope creep due to frequent schema and mapping changes, leading to rework, increased effort, and potential delays in delivery. | High | 2025-08-01 | Will | Potential delays in the overall project schedule which is impacting overall budget & cost control. | Freeze schema/mapping after design sign-off unless changes are business-critical & Establish a formal change control process for schema/mapping modifications. | TBC

## Dependencies
ID | Type | Date Raised | Description | Priority | Impact | Owner | Close By Date | Status | Comments
1 | Dependency | 2025-04-30 | Developers onboarding on Azure DevOps and allow access(read/write) to: - Azure Repo - Azure Boards - Azure Pipelines | H | Blocks development of Mule APIs. | Dan | 2025-05-08 | Close | 08/05: Got Access [Bell] Dan provided access on 2/5/2025 to Repo, Boards and Pipeline [Bell] CMMI board was create on 2/5/2025
2 | Dependency | 2025-04-30 | Developers access to SharePoint folder to read/write documents. | M | Blocks development of Mule APIs. | Paul | 2025-05-08 | Close | 08/05: Got Access Sindhu to check with Paul on Access to Prolifics DEV team.
3 | Dependency | 2025-04-30 | Developers onboarding on MuleSoft Anypoint Platform with designer and developer access. | H | Blocks development of Mule APIs. | Paul | 2025-05-01 | Close | 29/04: Access Granted.
4 | Dependency | 2025-04-30 | Signed Off HLD for VDS project. | H | Blocks design of Mule APIs. | Bell | 2025-05-02 | Close | 02/05: Bell shared HLD document. 01/05: Bell to share by EOD.
5 | Dependency | 2025-04-30 | Signed Off LLD for VDS project. | H | Blocks design of Mule APIs. | Bell | 2025-05-02 | Close | 02/05: Bell shared LLD document. 01/05: Bell to share by EOD.
6 | Dependency | 2025-04-30 | Signed Off Mapping Specifications for Delivery Notes interface. | H | Blocks development of Mule APIs. | Mezze\Bell | 2025-06-20 | Close | 09/05: Received all schema's from Mezze waiting for mapping spec's 08/05: First mapping version released 06/05: Sample messages and schema by Bell. 02/05: Sample message and JSON schema from mezze to be shared by EOD.
7 | Dependency | 2025-04-30 | Signed Off Mapping Specifications for Stock interface. | H | Blocks development of Mule APIs. | Mezze\Bell | 2025-06-13 | Close | 20/06: This is OOS. 09/05: Bell has created a sample schema which is considered to be Version 1, actual schema from Mezze is yet to be received. If any major changes from the sample schema it will be considered as Version 2. 08/05: First mapping version released. 06/05: Sample messages and schema shared by Bell. 02/05: Sample message and JSON schema from mezze shared by EOD.
8 | Dependency | 2025-04-30 | Signed Off Mapping Specifications for End Of Route interface. | H | Blocks development of Mule APIs. | Mezze\Bell | 2025-06-20 | Close | 09/05: No mappings received as on date 08/05: Bell followed up with Mezze and Waiting on Mezze (George Evans). They have agreed to share this information end of week. File will be uploaded to this location: https://samworthbrothers-my.sharepoint.com/:f:/r/personal/rebecca_farmer_samworthbrothers_co_uk/Documents/Documents/Mezze%20shared%20documents/Data%20file%20sharing?csf=1&web=1&e=peLlTb 08/05: First mapping version released. 02/05: Sample message and JSON schema from mezze shared by EOD.
9 | Dependency | 2025-04-30 | Signed Off Mapping Specifications for non food for now orders interface. | H | Blocks development of Mule APIs. | Mezze\Bell | 2025-06-17 | Close | 09/05: No mappings received as on date 08/05: First mapping version released. 02/05: Sample message and JSON schema from mezze shared by EOD.
10 | Dependency | 2025-04-30 | Signed Off Mapping Specifications for Customer Master Data interface. | H | Blocks development of Mule APIs. | Mezze\Bell | 2025-06-17 | Close | 09/05: No mappings received as on date 08/05: First mapping version released. 02/05: Sample message and JSON schema from mezze shared by EOD.
11 | Dependency | 2025-04-30 | Signed Off Mapping Specifications for Items Master Data interface. | H | Blocks development of Mule APIs. | Mezze\Bell | 2025-06-17 | Close | 09/05: No mappings received as on date 08/05: First mapping version released. 02/05: Sample message and JSON schema from mezze shared by EOD.
12 | Dependency | 2025-04-30 | Signed Off Mapping Specifications between alert CDM and Fresh Service. | H | Blocks development of Mule APIs. | Bell | 2025-06-19 | Close | 20/06: Using Existing CDM and Mappings for Fresh Service. 21/05: Ranjith to go through the mapping spec's and get back with the questions if any. 21/05: Mapping document for Alert CDM to Fresh Service (https://samworthbrothers.sharepoint.com/:x:/r/sites/PrgVDSMezzeePODsolution/Shared%20Documents/Main%20Project%20Channel/10_BA%20and%20Pre%20Work/30_Integration/Fresh%20Service/FreshServiceMapping.xlsx?d=waf9e844d5cd840da98777a06e0407772&csf=1&web=1&e=YCJwKr 09/05: No mappings received as on date. 08/05: Reference s-sb-relex-api\src\main\mule\global.xml, notificationMessage-report subflow has a reference to an alert sample. This is the cdm used for email alerts. I believe this has everything necessary for Fresh Service alerts. Just needs to be wrapped in a CloudEvent.
13 | Dependency | 2025-04-30 | Signed off user stories on Azure boards. | H | Blocks development of Mule APIs. | Rebecca | 2025-05-19 | Close | 20/05: Sindhu had call with Rebecca F, shared Monday.com board to Sindhu. Rebecca still working on full task list. 19/05: Sindhu to follow up with Rebecca on Monday.com tickets. 09/05: Ranjith will collate all the requirements and share it with SWB team, as per the discussions with Bell by 12/05. Bell to acknowledge. 06/05: Rebecca returns from annual leave on May 12.
14 | Dependency | 2025-04-30 | Dev & Test env connectivity details including security credentials for System 21 DB2 server | H | Blocks testing of Mule APIs in DEV & Test | Nell/Bell | 2025-05-09 | Close | 21/05: Requested access to dev i-series (to access via MuleSoft). https://itportal.samworthbrothers.co.uk/a/tickets/66259 20/05: Neil has requested us to use the following library PFFVSLIBF instead of LGNVSLIBF and that should give you access to the tables named with 'VDS' at the end of the table name like so, VAT001VDS, VAT002VDS 15/05: Got connectivity details for DEV environment and same is for TEST environment. 09/05: It is important to check DB2 connctivity to Mulesoft, If it fails this will be a blocker which impacts the entire project and we have to reconsider the design of this particular API (System) 07/05: Service Request created by Bell to Infosec team: https://itportal.samworthbrothers.co.uk/a/tickets/64996
15 | Dependency | 2025-04-30 | PROD env connectivity details including security credentials for System 21 DB2 server | H | Blocks testing of Mule APIs in PROD | Nell/Bell | TBC | Open
16 | Dependency | 2025-04-30 | Interface Specification/PostManCollection for Fresh Service APIs. | M | Blocks testing of Mule APIs | Bell | 2025-05-19 | Close | 21/05: Ranjith is going through the documenation and get back with clarifications if any. 20/05: API Documentation https://api.freshservice.com/#intro 20/05: Service request requesting for a Postman collection opened with Shamir. https://itportal.samworthbrothers.co.uk/a/tickets/66101 09/05: Will discuss with Bell after he is back to work. Acces to Fresh service for Raj/Ranjith
17 | Dependency | 2025-04-30 | Dev, Test and Live connectivity details including security credentials for Fresh Service. | M | Blocks testing of Mule APIs | Bell/Shamir | 2025-05-19 | Close | Received credentials for both DEV & TEST environments. 21/05: Request for credentials to access from muleSoft 20/05: Ticket closed on 9/5. Assuming, Fresh Service access was granted as per ticket. Please confirm access to Fresh Service Portal. Details below: Samworth ITSM Login URL - https://itportal.samworthbrothers.co.uk/ Prolifics / Samworth ITSM Tool Process - https://itportal.samworthbrothers.co.uk/a/solutions/articles/53000078494 Overall Agent Guide for Managing Tickets - https://itportal.samworthbrothers.co.uk/a/solutions/articles/53000028534 Also as discussed our Change Manage module in Freshservice is due to go live on May 19th. Please see guide for this below: https://itportal.samworthbrothers.co.uk/a/solutions/articles/53000072468 If any of you are still having access issues, please quote the ticket #64597 to Shamir for follow-up. 06/05: Bell has requested for Fresh Service console access: https://itportal.samworthbrothers.co.uk/a/tickets/64597& Requested API access and keys : https://itportal.samworthbrothers.co.uk/a/tickets/64596
18 | Dependency | 2025-04-30 | Prod connectivity details including security credentials for Fresh Service. | M | Blocks testing of Mule APIs | Bell/Shamir | TBC | Open
19 | Dependency | 2025-04-30 | Dev, Test and Live Azure connectivity details(tenantId, clientId, clientSecret, issuer) to configure OAuth 2.0. | M | Blocks testing of Mule APIs | Jonathan/Bell | 2025-05-23 | Close | 23/05: Received details. 09/05: Disucussed with Bell, as a work around we will use client ID enforcement.
20 | Dependency | 2025-04-30 | Dev env Azure Key Vault details(tenantId, clientId, clientSecret) to connect with Azure Key Vault provider. | M | Blocks development of Mule APIs. | Jonathan/Bell | 2025-05-15 | Close | 15/05: Got the details for all environments.. 09/05: Discussed with Bell as a workaround, In absence of Azure Key Vault connection we use Mulesoft encryption to store the passowrd.
21 | Dependency | 2025-04-30 | Dev, Test and Live connectivity details(storage account, access key, signature) for Azure Blob storage service. | M | Blocks development of Mule APIs. | Shaun/Bell | 2025-05-15 | Close | 15/05: Got the required details from Dan for all environments. (Use same for DEV and TEST) 09/05: Blocks both development & testing, required by mid of next week. 06/05: Bell has sent request to Shaun and Jonathon, cc'd Paul Lanman
22 | Dependency | 2025-04-30 | Dev, Test and Live connectivity details(username, paswords, keys) for SamWorth SFTP server. | M | Blocks development of Mule APIs. | Jonathan Smith/Bell | 2025-06-03 | Close | 20/05: Bell to provide SFTP details. 15/05: Need to check with Bell if we need SFTP? 09/05: Required at the time of Build, probably by next week. 06/05: Bell has sent request to Jonathan Smith.
23 | Dependency | 2025-04-30 | Build prioritization order between different interfaces. | M | Blocks development of Mule APIs. | Bell | 2025-05-01 | Close | Delivery Notes, Stocks, Notes - exp Non food for now master and transaction - items, customers, orders DB2 System API Fresh Service integration
24 | Dependency | 2025-05-02 | Citrix access to developers | M | Blocks Testing. | Bell | 2025-06-13 | Close | 13/06: Got access to Citrix. 06/06: UK team got access to Citrix, India team didn’t. 08/05: As a work around Bell suggested to work on our (Prolifics) local systems. 02/05: Service Request ticket for follow up: https://itportal.samworthbrothers.co.uk/a/tickets/64420
25 | Dependency | 2025-06-02 | SFTP Server Access | M | Blocks Testing. | Bell | 2025-06-06 | Close
26 | Dependency | 2025-06-02 | Nexus access to import Azure KeyVault Properties provider | M | Blocks development of Mule APIs. | Bell | 2025-06-03 | Close
27 | Dependency | 2022-06-19 | Table Journaling on System 21 DB2 tables. | M | Blocks Testing. | Bell | 2025-07-02 | Close

## Decisions
S.No | Date of Discussion | Raised By | Description | Decisions
1 | 2025-05-19 | Ranjith Vadiyala | APIs Prolifics build will be running on 4.9 versions and the existing JSON logger is not supported in 4.9 so we may have to use Mulesoft logger components | 23/05: Concluded to use Mulesfot logger. 21/05: Noticed recent updates on JSON logger in exchange, need to confirm if anyone is updating. 20/05: Raj suggested that out of the box logger could be an option instead of JSON logger. Is it a question of re-compiling the json logger module with Java 17 and the Mule Runtime 4.9?
2 | 2025-05-19 | Ranjith Vadiyala | Implementation of alerting – We must plan to discuss on the CDM message structures and where to push. Assuming pushing into a Queue via Exchange with a CDM. | 23/05: Concluded to use the existing CDM messages. 20/05: Mapping specifications are inplace. Ranjith to go through and get back if any questions. 20/05: Ranjith is looking for Fresh Service API mapping specifications. Based on our conversation yesterday (19/5/2025) can we use the same CDM as what is used for email alerts? I will look to map the CDM to the Fresh Service alert object in the Fresh Service API.
3 | 2025-05-19 | Ranjith Vadiyala | Implementing error-handling – We use existing error handling as is. Based the issues we encounter we put more efforts to modify the logic. FYI Mule 4.4 supports error.suppressedErrors.errorType.namespace[0] It is not available in 4.6 and later versions. | 23/05: Concluded that we will use the existing framework as is, and will add new logics only if the existing one's doesn't support the context. 20/05: Change in error structures/object names should be replaced. Current implementation of error handligh is quite complex, can be simplified further. Raj/Ranjith to discuss and get back What value does this, error.suppressedErrors.errorType.namespace[0], return? Is it just a question of fetching this value from a different path?
4 | 2025-05-19 | Ranjith Vadiyala | Azure Blob Storage VS SFTP decision on file-mover solution to be concluded | 23/05: Concluded that mezze will receive the files on SFTP, details are yet to be provided by SB. 20/05: Mezze is going to pick up from SFTP and deliver to SFTP server. SFTP details to be provided. Could you please elaborate on this?
5 | 2025-05-19 | Ranjith Vadiyala | Every Rest API HTTP Listener uses a unique JKS file in TLS configurations which is hard to maintain, comeup with a plan to avoid such things | 23/05: Concluded that no JKS/TLS configurations will be used with in mule APIs. 20/05: Raj to review the approach discussed during the call and rediscuss. Need secure Key details of JKS. - Speak with Shubh to get that information as part of handover. Raj and Ranjith, since Private Space has SSL configured, is it necessary to run SSL at the API level? No PII or PCI data being transmitted?
6 | 2025-05-19 | Ranjith Vadiyala | Master-data Process API name confirmation? We used p-sb-master-data-export-scheduler-app. I now think p-sb-master-data-nrt-scheduler-app may sounds better, where nrt mean - near real time. | 23/05: Concluded that "p-sb-scheduler-app" can be used. 20/05: instead of near real time, can be scheduler app (p-sb-master-data-scheduler-app). Can be divided in 2 parts - Scheduler & implementation I would recommend using: p-sb-lowlatency-scheduler-app or p-sb-ll-scheduler-app
7 | 2025-05-19 | Ranjith Vadiyala | Ax-Customer-SAPI, Ax-Items-SAPI these system APIs have restrictions of processing Max of 50 items/records which means we either have to save the CSV data in chucks to a variable(this is our current implementation). we also have an open option to explore REST ends from Azure which uses append-blob (Not supported by the AzureBlobStorage connector). trying to understand why the restrictions is in place & can we avoid it? | 28/05: Concluded to use Azure Data Lake. 23/05: Waiting for OAUTH credentials to access Azure REST APIs. 20/05: Concluded to use the REST API call to append to blob.
8 | 2025-05-20 | Ranjith Vadiyala | Key Vault integration Decision | 05/06: Concluded to use Secure properties for local and DEV testing, Once CITRIX is sorted we can move it to KeyVault. 29/05: Concluded that we will go with Azure Keyvault OOB (Out of box) connector. 23/05: We mentioned we use Azure Keyvault OOB connector, Now we want to go with DevOps as this option is costly. 20/05: Raj has shared the document to Bell. Need to further discuss. 20/05: Discuss on pro & cons of each option and arrive at the best ap
9 | 2025-06-20 | Ranjith Vadiyala | Proposed mapping field limitation decisions on Mezze Exp API & System 21 APIs from SB to be concluded. | 24/06: Concluded to make use of override schemas

## Action Items
ID | Action Item | Owner | Status | Comments by SB | Comments by Prolifics | Target Date | Date Completed
1 | Azure Key Vault integration | Prolifics | Closed |  | Discuss on pro & cons of each option and arrive at the best approach. Concluded that we will go with Azure Keyvault OOB (Out of box) connector. | 2025-05-23 | 2025-05-23
2 | DB2 Connectivity Check | Prolifics | Closed |  | Conduct connectivity and data insertion tests for the DB2 database to ensure successful communication and data flow. | 2025-05-15 | 2025-05-15
3 | Error Handling | Prolifics | Closed |  | We assumed we use it as is from existing design. But we noticed there are some error cases that are not handled and also the properties files not used. We are patching based on our needs. | 15-05-2025 | 2025-05-15
4 | Azure Blob Storage Append Operations | Prolifics | Closed |  | Azure Data Lake connector to be used. | 2025-05-28 | 2025-05-28
5 | Schema Changes & Deployment Impact | Prolifics | Open |  | Due to ongoing changes in incremental schemas, frequent code redeployment and testing are required to validate each update. - Mezze (we have to fix the broken DN schema and got 2 versions of Stock transfer schema), System21(got 2 versions of table names). | 2025-06-13 | 2025-06-13
6 | System 21 | Prolifics | Closed |  | Initial assumption was one Stored Procedure call inserts into all tables but not we decided to segregate the approach. | 19-05-2025 | 2025-05-19
7 | Current pipelines does not support 4.9 runtime & JAVA 17 | Prolifics | Closed |  | To work with new maven version and mule 4.9 runtime. We made the changes and we currently are able to deploy Mezze exp API using updated pipelines. | 2025-05-22 | 2025-05-22
8 | Azure Table Storage | Prolifics | Closed |  | Azure Table Storage is replated with Cosmos DB | 2025-06-02 | 2025-06-02

## POC
ID | POC | Description | Resource | Start Date | Target Date | Status | Comments | Time Spent
1 | Key vault integration | To retrive the values from Key store via CI/CD pipeline. | Raj Chaudhary |  |  | On Hold | SB conluded to go with option 1 and reading the keys at flow level.
2 | Azure Data Lake connector | To check append file operations in Azure BLOB. | Narendra Battineni | 2025-05-27 | 2025-05-28 | Completed |  | 8 Hrs
3 | Azure Table storage | To check insertion of data into Azure tables to replace object store in mule flows | Narendra Battineni | 2025-05-22 | 2025-05-22 | Completed | SB conluded to go with Cosmos DB for better design usability. | 6 Hrs
4 | Azure Cosmos DB | To check insertion of data into Azure tables to replace object store in mule flows | Raj Chaudhary | 2025-05-28 | 2025-05-29 | Completed
5 | App Insights | To check the process of sending logs from mulesoft to azure app insights. | Narendra Battineni | 2025-05-21 | 2025-05-21 | Completed |  | 4 Hrs

## Change Requests
S.No | Task# | Description | OnSite | Offshore | Status
1 | Task-129 | Setup SFTP connection with key pair method (DEV) | 2 Hrs |  | Active
2 | Task-132 | s-sb-filemover-api: Modify configurations in SFTP connection with key pair method in dev environment (UAT) | 5 Hrs | 2 Hrs (Sruthi) | Active
3 | Task-130 | Modify the container, directory structure, and file paths in the sbdatalakedev Azure account | 3 Hrs | 3 Hrs (Sasi) | Proposed
4 | Task-131 | p-sb-scheduler-app : Modify the container, directory structure, and file paths in the sbdatalakedev Azure account |  |  | Active
5 | Task- 140 | Mezze items - change to mapping | 2.5 Hrs | 4 Hrs (Sasi) | Proposed
6 | Task-143 | p-sb-scheduler-app: Items csv file mapping changes for mezz | 1 Hr |  | Active
7 | Task-147 | p-sb-scheduler-app : Delivery Date format in sales order for mezze | 1 Hr |  | Active
8 | Task-148 | Mezze Customers - change to mapping | 1 Hr |  | Proposed
9 | Task-149 | p-sb-scheduler-app: Customers csv file mapping changes for mezze | 1 Hr |  | Active
Other Tasks
| 1 | Daily Stand Ups | 10 Hrs | 5 Hrs
| 2 | Modify Pipelines for UAT deployments | 3 Hrs
| 3 | Order Changes (AX-Sales Orders API/Scheduler API) | 1 Hr | 3 Hrs